## L2 Schedule
ID | WBS | Activity Name | Dur | Pred | Succ | ES | EF | LS | LF | TF | FF | Crit | Start Date | Finish Date | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027 | Feb-2027 | Mar-2027 | Apr-2027 | May-2027 | Jun-2027 | Jul-2027 | Aug-2027 | Sep-2027 | Oct-2027 | Nov-2027 | Dec-2027
1 | 1.1 | Project Kick-off & Charter | 5 |  | 2, 7, 10, 11, 12, 13 | 0 | 5 | 0 | 5 | 0 | 0 | YES | 2026-05-11 | 2026-05-16
2 | 1.2 | PMO Establishment & Governance | 8 | 1 | 3, 4 | 5 | 13 | 561 | 569 | 556 | 0 | NO | 2026-05-16 | 2026-05-24
3 | 1.3 | Project Controls & Baselines | 8 | 2 | 5 | 13 | 21 | 569 | 577 | 556 | 0 | NO | 2026-05-24 | 2026-06-01
4 | 1.4 | Risk Management Framework | 6 | 2 |  | 13 | 19 | 587 | 593 | 574 | 574 | NO | 2026-05-24 | 2026-05-30
5 | 1.5 | Monthly Steering Reviews | 8 | 3 | 6 | 21 | 29 | 577 | 585 | 556 | 0 | NO | 2026-06-01 | 2026-06-09
6 | 1.6 | Final Project Report & Closeout | 8 | 5 |  | 29 | 37 | 585 | 593 | 556 | 556 | NO | 2026-06-09 | 2026-06-17
7 | 2.1 | Term Sheet Negotiation | 12 | 1 | 8 | 5 | 17 | 5 | 17 | 0 | 0 | YES | 2026-05-16 | 2026-05-28
8 | 2.2 | Definitive Agreement Drafting | 15 | 7 | 9 | 17 | 32 | 17 | 32 | 0 | 0 | YES | 2026-05-28 | 2026-06-12
9 | 2.3 | Legal Review & Revisions | 10 | 8 | 14, 15, 16 | 32 | 42 | 32 | 42 | 0 | 0 | YES | 2026-06-12 | 2026-06-22
10 | 2.4 | Technical Due Diligence | 15 | 1 |  | 5 | 20 | 578 | 593 | 573 | 573 | NO | 2026-05-16 | 2026-05-31
11 | 2.5 | Financial Due Diligence | 12 | 1 | 14, 15 | 5 | 17 | 30 | 42 | 25 | 25 | NO | 2026-05-16 | 2026-05-28
12 | 2.6 | Environmental Due Diligence | 12 | 1 |  | 5 | 17 | 581 | 593 | 576 | 576 | NO | 2026-05-16 | 2026-05-28
13 | 2.7 | Security Due Diligence | 10 | 1 |  | 5 | 15 | 583 | 593 | 578 | 578 | NO | 2026-05-16 | 2026-05-26
14 | 2.8 | Equity Commitment Letters | 10 | 9, 11 | 17 | 42 | 52 | 60 | 70 | 18 | 18 | NO | 2026-06-22 | 2026-07-02
15 | 2.9 | Debt Financing Arrangement | 28 | 9, 11 | 17 | 42 | 70 | 42 | 70 | 0 | 0 | YES | 2026-06-22 | 2026-07-20
16 | 2.10 | Insurance Placement | 10 | 9 | 17 | 42 | 52 | 60 | 70 | 18 | 18 | NO | 2026-06-22 | 2026-07-02
17 | 2.11 | Financial Close Milestone | 0 | 14, 15, 16 | 18, 19, 20, 21, 23, 24, 25, 26, 27, 28, 29, 34, 39, 42, 43, 46 | 70 | 70 | 70 | 70 | 0 | 0 | YES | 2026-07-20 | 2026-07-20 |  |  | ◆
18 | 3.1 | Title Verification & Insurance | 6 | 17 |  | 70 | 76 | 587 | 593 | 517 | 517 | NO | 2026-07-20 | 2026-07-26
19 | 3.2 | Boundary & ALTA Survey | 10 | 17 | 30 | 70 | 80 | 176 | 186 | 106 | 5 | NO | 2026-07-20 | 2026-07-30
20 | 3.3 | Easement & Access Confirmation | 6 | 17 |  | 70 | 76 | 587 | 593 | 517 | 517 | NO | 2026-07-20 | 2026-07-26
21 | 3.4 | Phase I Environmental Assessment | 12 | 17 | 22 | 70 | 82 | 561 | 573 | 491 | 0 | NO | 2026-07-20 | 2026-08-01
22 | 3.5 | Phase II ESA (if required) | 20 | 21 |  | 82 | 102 | 573 | 593 | 491 | 491 | NO | 2026-08-01 | 2026-08-21
23 | 3.6 | Wetlands Delineation | 12 | 17 | 30 | 70 | 82 | 174 | 186 | 104 | 3 | NO | 2026-07-20 | 2026-08-01
24 | 3.7 | Endangered Species Survey | 15 | 17 | 30 | 70 | 85 | 171 | 186 | 101 | 0 | NO | 2026-07-20 | 2026-08-04
25 | 3.8 | Cultural Heritage Assessment | 12 | 17 | 30 | 70 | 82 | 174 | 186 | 104 | 3 | NO | 2026-07-20 | 2026-08-01
26 | 3.9 | Geotechnical Investigation | 15 | 17 | 49, 55 | 70 | 85 | 75 | 90 | 5 | 5 | NO | 2026-07-20 | 2026-08-04
27 | 3.10 | Topographic Survey | 10 | 17 | 57 | 70 | 80 | 239 | 249 | 169 | 10 | NO | 2026-07-20 | 2026-07-30
28 | 3.11 | Hydrology & Drainage Study | 12 | 17 | 48 | 70 | 82 | 252 | 264 | 182 | 8 | NO | 2026-07-20 | 2026-08-01
29 | 3.12 | Zoning & Land Use Verification | 6 | 17 | 30 | 70 | 76 | 180 | 186 | 110 | 9 | NO | 2026-07-20 | 2026-07-26
30 | 3.13 | Development Permit Application | 20 | 19, 23, 24, 25, 29 | 31 | 85 | 105 | 186 | 206 | 101 | 0 | NO | 2026-08-04 | 2026-08-24
31 | 3.14 | Development Permit Approval | 35 | 30 | 32, 45, 135 | 105 | 140 | 206 | 241 | 101 | 0 | NO | 2026-08-24 | 2026-09-28
32 | 3.15 | Building Permit Application | 12 | 31 | 33 | 140 | 152 | 561 | 573 | 421 | 0 | NO | 2026-09-28 | 2026-10-10
33 | 3.16 | Building Permit Approval | 20 | 32 | 45 | 152 | 172 | 573 | 593 | 421 | 37 | NO | 2026-10-10 | 2026-10-30
34 | 3.17 | TFO Pre-Application Meeting | 8 | 17 | 35 | 70 | 78 | 391 | 399 | 321 | 0 | NO | 2026-07-20 | 2026-07-28
35 | 3.18 | TFO Feasibility Study | 28 | 34 | 36 | 78 | 106 | 399 | 427 | 321 | 0 | NO | 2026-07-28 | 2026-08-25
36 | 3.19 | TFO System Impact Study | 40 | 35 | 37 | 106 | 146 | 427 | 467 | 321 | 0 | NO | 2026-08-25 | 2026-10-04
37 | 3.20 | TFO Facilities Study | 28 | 36 | 38 | 146 | 174 | 467 | 495 | 321 | 0 | NO | 2026-10-04 | 2026-11-01
38 | 3.21 | TFO Interconnection Agreement | 20 | 37 | 41, 234 | 174 | 194 | 495 | 515 | 321 | 0 | NO | 2026-11-01 | 2026-11-21
39 | 3.22 | LDC Service Application | 10 | 17 | 40 | 70 | 80 | 553 | 563 | 483 | 0 | NO | 2026-07-20 | 2026-07-30
40 | 3.23 | LDC Transformer Sizing Study | 15 | 39 | 41 | 80 | 95 | 563 | 578 | 483 | 99 | NO | 2026-07-30 | 2026-08-14
41 | 3.24 | LDC Service Agreement Execution | 15 | 40, 38 | 45 | 194 | 209 | 578 | 593 | 384 | 0 | NO | 2026-11-21 | 2026-12-06
42 | 3.25 | Indigenous Consultation & Agreement | 50 | 17 | 45 | 70 | 120 | 543 | 593 | 473 | 89 | NO | 2026-07-20 | 2026-09-08
43 | 3.26 | Community Engagement Program | 35 | 17 | 44 | 70 | 105 | 543 | 578 | 473 | 0 | NO | 2026-07-20 | 2026-08-24
44 | 3.27 | Municipal Council Presentation | 15 | 43 |  | 105 | 120 | 578 | 593 | 473 | 473 | NO | 2026-08-24 | 2026-09-08
45 | 3.28 | Site Development Complete Milestone | 0 | 31, 33, 41, 42 |  | 209 | 209 | 593 | 593 | 384 | 384 | NO | 2026-12-06 | 2026-12-06 | [7 empty] | ◆
46 | 4.1 | Campus Master Plan | 20 | 17 | 47, 48, 49, 57, 236, 237 | 70 | 90 | 70 | 90 | 0 | 0 | YES | 2026-07-20 | 2026-08-09
47 | 4.2 | Traffic Impact Study | 15 | 46 |  | 90 | 105 | 578 | 593 | 488 | 488 | NO | 2026-08-09 | 2026-08-24
48 | 4.3 | Stormwater Management Plan | 15 | 46, 28 | 139 | 90 | 105 | 264 | 279 | 174 | 164 | NO | 2026-08-09 | 2026-08-24
49 | 4.4 | Concept Design | 15 | 46, 26 | 50, 54, 77 | 90 | 105 | 90 | 105 | 0 | 0 | YES | 2026-08-09 | 2026-08-24
50 | 4.5 | Schematic Design | 20 | 49 | 51, 58, 64, 74, 78 | 105 | 125 | 105 | 125 | 0 | 0 | YES | 2026-08-24 | 2026-09-13
51 | 4.6 | Design Development | 25 | 50 | 52, 63, 68, 69, 70, 71, 79 | 125 | 150 | 125 | 150 | 0 | 0 | YES | 2026-09-13 | 2026-10-08
52 | 4.7 | Construction Documents | 40 | 51 | 53, 80, 82, 119, 124 | 150 | 190 | 150 | 190 | 0 | 0 | YES | 2026-10-08 | 2026-11-17
53 | 4.8 | Permit Drawings Package | 15 | 52 | 81 | 190 | 205 | 576 | 591 | 386 | 0 | NO | 2026-11-17 | 2026-12-02
54 | 4.9 | Structural Concept Design | 10 | 49 | 55, 56 | 105 | 115 | 269 | 279 | 164 | 0 | NO | 2026-08-24 | 2026-09-03
55 | 4.10 | Foundation Design | 15 | 54, 26 | 141 | 115 | 130 | 279 | 294 | 164 | 164 | NO | 2026-09-03 | 2026-09-18
56 | 4.11 | Structural Steel Design | 20 | 54 | 144 | 115 | 135 | 309 | 329 | 194 | 194 | NO | 2026-09-03 | 2026-09-23
57 | 4.12 | Civil Site Design | 20 | 46, 27 | 138 | 90 | 110 | 249 | 269 | 159 | 159 | NO | 2026-08-09 | 2026-08-29
58 | 4.13 | Mechanical Concept Design | 15 | 50 | 59, 60, 61, 62 | 125 | 140 | 274 | 289 | 149 | 0 | NO | 2026-09-13 | 2026-09-28
59 | 4.14 | Chiller Plant Design | 20 | 58 | 66, 89, 150, 151 | 140 | 160 | 377 | 397 | 237 | 0 | NO | 2026-09-28 | 2026-10-18
60 | 4.15 | CDU & Secondary Loop Design | 20 | 58 | 109, 155 | 140 | 160 | 289 | 309 | 149 | 0 | NO | 2026-09-28 | 2026-10-18
61 | 4.16 | CRAH/FWU Design | 15 | 58 | 114 | 140 | 155 | 470 | 485 | 330 | 0 | NO | 2026-09-28 | 2026-10-13
62 | 4.17 | Plumbing & Drainage Design | 15 | 58 | 153 | 140 | 155 | 395 | 410 | 255 | 209 | NO | 2026-09-28 | 2026-10-13
63 | 4.18 | Fire Protection Design | 20 | 51 | 153, 154 | 150 | 170 | 390 | 410 | 240 | 194 | NO | 2026-10-08 | 2026-10-28
64 | 4.19 | Single Line Diagram Development | 15 | 50 | 65, 66, 67, 68 | 125 | 140 | 251 | 266 | 126 | 0 | NO | 2026-09-13 | 2026-09-28
65 | 4.20 | Substation Design | 20 | 64 | 94, 149, 158 | 140 | 160 | 289 | 309 | 149 | 0 | NO | 2026-09-28 | 2026-10-18
66 | 4.21 | Generator Integration Design | 15 | 64, 59 | 84 | 160 | 175 | 397 | 412 | 237 | 0 | NO | 2026-10-18 | 2026-11-02
67 | 4.22 | UPS Distribution Design | 15 | 64 | 99 | 140 | 155 | 452 | 467 | 312 | 0 | NO | 2026-09-28 | 2026-10-13
68 | 4.23 | Busduct & Rack Power Design | 20 | 64, 51 | 104, 127, 131 | 150 | 170 | 266 | 286 | 116 | 0 | NO | 2026-10-08 | 2026-10-28
69 | 4.24 | Lighting & Emergency Design | 10 | 51 |  | 150 | 160 | 583 | 593 | 433 | 433 | NO | 2026-10-08 | 2026-10-18
70 | 4.25 | BMS/EPMS/SCADA Design | 30 | 51 | 165 | 150 | 180 | 415 | 445 | 265 | 219 | NO | 2026-10-08 | 2026-11-07
71 | 4.26 | Security Layer Design | 20 | 51 | 72, 73, 126, 233 | 150 | 170 | 520 | 540 | 370 | 0 | NO | 2026-10-08 | 2026-10-28
72 | 4.27 | Access Control Design | 15 | 71 | 166 | 170 | 185 | 563 | 578 | 393 | 229 | NO | 2026-10-28 | 2026-11-12
73 | 4.28 | CCTV & Monitoring Design | 10 | 71 | 166 | 170 | 180 | 568 | 578 | 398 | 234 | NO | 2026-10-28 | 2026-11-07
74 | 4.29 | ANR Room Design | 15 | 50 | 75, 76, 152 | 125 | 140 | 400 | 415 | 275 | 0 | NO | 2026-09-13 | 2026-09-28
75 | 4.30 | Fiber Entry Design | 10 | 74 | 133, 235 | 140 | 150 | 415 | 425 | 275 | 0 | NO | 2026-09-28 | 2026-10-08
76 | 4.31 | Campus Network Backbone Design | 15 | 74 |  | 140 | 155 | 578 | 593 | 438 | 438 | NO | 2026-09-28 | 2026-10-13
77 | 4.32 | Concept Design Review | 2 | 49 |  | 105 | 107 | 591 | 593 | 486 | 486 | NO | 2026-08-24 | 2026-08-26
78 | 4.33 | 30% Design Review | 2 | 50 |  | 125 | 127 | 591 | 593 | 466 | 466 | NO | 2026-09-13 | 2026-09-15
79 | 4.34 | 60% Design Review | 2 | 51 |  | 150 | 152 | 591 | 593 | 441 | 441 | NO | 2026-10-08 | 2026-10-10
80 | 4.35 | 90% Design Review | 2 | 52 |  | 190 | 192 | 591 | 593 | 401 | 401 | NO | 2026-11-17 | 2026-11-19
81 | 4.36 | IFC Design Review | 2 | 53 | 83 | 205 | 207 | 591 | 593 | 386 | 0 | NO | 2026-12-02 | 2026-12-04
82 | 4.37 | FM Global Design Review | 15 | 52 | 83 | 190 | 205 | 578 | 593 | 388 | 2 | NO | 2026-11-17 | 2026-12-02
83 | 4.38 | Design Complete Milestone | 0 | 81, 82 |  | 207 | 207 | 593 | 593 | 386 | 386 | NO | 2026-12-04 | 2026-12-04 | [7 empty] | ◆
84 | 5.1 | Generator RFQ Issue | 8 | 66 | 85 | 175 | 183 | 412 | 420 | 237 | 0 | NO | 2026-11-02 | 2026-11-10
85 | 5.2 | Generator Bid Evaluation | 8 | 84 | 86 | 183 | 191 | 420 | 428 | 237 | 0 | NO | 2026-11-10 | 2026-11-18
86 | 5.3 | Generator PO Placement | 5 | 85 | 87 | 191 | 196 | 428 | 433 | 237 | 0 | NO | 2026-11-18 | 2026-11-23
87 | 5.4 | Generator Manufacturing | 120 | 86 | 88 | 196 | 316 | 433 | 553 | 237 | 0 | NO | 2026-11-23 | 2027-03-23
88 | 5.5 | Generator Delivery (FAT + Shipping) | 25 | 87 | 134, 156 | 316 | 341 | 553 | 578 | 237 | 0 | NO | 2027-03-23 | 2027-04-17
89 | 5.6 | Chiller RFQ Issue | 8 | 59 | 90 | 160 | 168 | 438 | 446 | 278 | 0 | NO | 2026-10-18 | 2026-10-26
90 | 5.7 | Chiller Bid Evaluation | 8 | 89 | 91 | 168 | 176 | 446 | 454 | 278 | 0 | NO | 2026-10-26 | 2026-11-03
91 | 5.8 | Chiller PO Placement | 5 | 90 | 92 | 176 | 181 | 454 | 459 | 278 | 0 | NO | 2026-11-03 | 2026-11-08
92 | 5.9 | Chiller Manufacturing | 90 | 91 | 93 | 181 | 271 | 459 | 549 | 278 | 0 | NO | 2026-11-08 | 2027-02-06
93 | 5.10 | Chiller Delivery (FAT + Shipping) | 20 | 92 | 134, 160 | 271 | 291 | 549 | 569 | 278 | 50 | NO | 2027-02-06 | 2027-02-26
94 | 5.11 | Switchgear RFQ Issue | 8 | 65 | 95 | 160 | 168 | 309 | 317 | 149 | 0 | NO | 2026-10-18 | 2026-10-26
95 | 5.12 | Switchgear Bid Evaluation | 8 | 94 | 96 | 168 | 176 | 317 | 325 | 149 | 0 | NO | 2026-10-26 | 2026-11-03
96 | 5.13 | Switchgear PO Placement | 5 | 95 | 97 | 176 | 181 | 325 | 330 | 149 | 0 | NO | 2026-11-03 | 2026-11-08
97 | 5.14 | Switchgear Manufacturing | 75 | 96 | 98 | 181 | 256 | 330 | 405 | 149 | 0 | NO | 2026-11-08 | 2027-01-22
98 | 5.15 | Switchgear Delivery (FAT + Shipping) | 20 | 97 | 134, 157 | 256 | 276 | 405 | 425 | 149 | 65 | NO | 2027-01-22 | 2027-02-11
99 | 5.16 | UPS RFQ Issue | 8 | 67 | 100 | 155 | 163 | 467 | 475 | 312 | 0 | NO | 2026-10-13 | 2026-10-21
100 | 5.17 | UPS Bid Evaluation | 8 | 99 | 101 | 163 | 171 | 475 | 483 | 312 | 0 | NO | 2026-10-21 | 2026-10-29
101 | 5.18 | UPS PO Placement | 5 | 100 | 102 | 171 | 176 | 483 | 488 | 312 | 0 | NO | 2026-10-29 | 2026-11-03
102 | 5.19 | UPS Manufacturing | 75 | 101 | 103 | 176 | 251 | 488 | 563 | 312 | 0 | NO | 2026-11-03 | 2027-01-17
103 | 5.20 | UPS Delivery (FAT + Shipping) | 20 | 102 | 134, 159 | 251 | 271 | 563 | 583 | 312 | 70 | NO | 2027-01-17 | 2027-02-06
104 | 5.21 | Busduct/HAC RFQ Issue | 8 | 68 | 105 | 170 | 178 | 286 | 294 | 116 | 0 | NO | 2026-10-28 | 2026-11-05
105 | 5.22 | Busduct/HAC Bid Evaluation | 8 | 104 | 106 | 178 | 186 | 294 | 302 | 116 | 0 | NO | 2026-11-05 | 2026-11-13
106 | 5.23 | Busduct/HAC PO Placement | 5 | 105 | 107 | 186 | 191 | 302 | 307 | 116 | 0 | NO | 2026-11-13 | 2026-11-18
107 | 5.24 | Busduct/HAC Manufacturing | 60 | 106 | 108 | 191 | 251 | 307 | 367 | 116 | 0 | NO | 2026-11-18 | 2027-01-17
108 | 5.25 | Busduct/HAC Delivery | 12 | 107 | 134, 163 | 251 | 263 | 367 | 379 | 116 | 78 | NO | 2027-01-17 | 2027-01-29
109 | 5.26 | CDU RFQ Issue | 8 | 60 | 110 | 160 | 168 | 309 | 317 | 149 | 0 | NO | 2026-10-18 | 2026-10-26
110 | 5.27 | CDU Bid Evaluation | 8 | 109 | 111 | 168 | 176 | 317 | 325 | 149 | 0 | NO | 2026-10-26 | 2026-11-03
111 | 5.28 | CDU PO Placement | 5 | 110 | 112 | 176 | 181 | 325 | 330 | 149 | 0 | NO | 2026-11-03 | 2026-11-08
112 | 5.29 | CDU Manufacturing | 75 | 111 | 113 | 181 | 256 | 330 | 405 | 149 | 0 | NO | 2026-11-08 | 2027-01-22
113 | 5.30 | CDU Delivery (FAT + Shipping) | 20 | 112 | 134, 161 | 256 | 276 | 405 | 425 | 149 | 65 | NO | 2027-01-22 | 2027-02-11
114 | 5.31 | CRAH/FWU RFQ Issue | 8 | 61 | 115 | 155 | 163 | 485 | 493 | 330 | 0 | NO | 2026-10-13 | 2026-10-21
115 | 5.32 | CRAH/FWU Bid Evaluation | 8 | 114 | 116 | 163 | 171 | 493 | 501 | 330 | 0 | NO | 2026-10-21 | 2026-10-29
116 | 5.33 | CRAH/FWU PO Placement | 5 | 115 | 117 | 171 | 176 | 501 | 506 | 330 | 0 | NO | 2026-10-29 | 2026-11-03
117 | 5.34 | CRAH/FWU Manufacturing | 60 | 116 | 118 | 176 | 236 | 506 | 566 | 330 | 0 | NO | 2026-11-03 | 2027-01-02
118 | 5.35 | CRAH/FWU Delivery | 12 | 117 | 134, 162 | 236 | 248 | 566 | 578 | 330 | 93 | NO | 2027-01-02 | 2027-01-14
119 | 5.36 | GC Prequalification | 12 | 52 | 120 | 190 | 202 | 190 | 202 | 0 | 0 | YES | 2026-11-17 | 2026-11-29
120 | 5.37 | GC RFP Issue | 12 | 119 | 121 | 202 | 214 | 202 | 214 | 0 | 0 | YES | 2026-11-29 | 2026-12-11
121 | 5.38 | GC Bid Evaluation | 12 | 120 | 122, 125, 126 | 214 | 226 | 214 | 226 | 0 | 0 | YES | 2026-12-11 | 2026-12-23
122 | 5.39 | GC Contract Negotiation | 12 | 121 | 123 | 226 | 238 | 226 | 238 | 0 | 0 | YES | 2026-12-23 | 2027-01-04
123 | 5.40 | GC Contract Award | 3 | 122 | 134, 135 | 238 | 241 | 238 | 241 | 0 | 0 | YES | 2027-01-04 | 2027-01-07
124 | 5.41 | MEP Subcontract RFP | 12 | 52 | 125 | 190 | 202 | 571 | 583 | 381 | 24 | NO | 2026-11-17 | 2026-11-29
125 | 5.42 | MEP Subcontract Award | 10 | 124, 121 | 134 | 226 | 236 | 583 | 593 | 357 | 105 | NO | 2026-12-23 | 2027-01-02
126 | 5.43 | Security Subcontract Award | 10 | 71, 121 | 134 | 226 | 236 | 583 | 593 | 357 | 105 | NO | 2026-12-23 | 2027-01-02
127 | 5.44 | Rack & Infrastructure RFQ | 8 | 68 | 128 | 170 | 178 | 351 | 359 | 181 | 0 | NO | 2026-10-28 | 2026-11-05
128 | 5.45 | Rack PO Placement | 5 | 127 | 129 | 178 | 183 | 359 | 364 | 181 | 0 | NO | 2026-11-05 | 2026-11-10
129 | 5.46 | Rack Manufacturing | 35 | 128 | 130 | 183 | 218 | 364 | 399 | 181 | 0 | NO | 2026-11-10 | 2026-12-15
130 | 5.47 | Rack Delivery to Site | 10 | 129 | 164 | 218 | 228 | 399 | 409 | 181 | 181 | NO | 2026-12-15 | 2026-12-25
131 | 5.48 | Cable Tray RFQ | 8 | 68 | 132 | 170 | 178 | 373 | 381 | 203 | 0 | NO | 2026-10-28 | 2026-11-05
132 | 5.49 | Cable Tray PO & Delivery | 28 | 131 | 164 | 178 | 206 | 381 | 409 | 203 | 203 | NO | 2026-11-05 | 2026-12-03
133 | 5.50 | Fiber Cable Procurement | 15 | 75 | 167 | 150 | 165 | 425 | 440 | 275 | 174 | NO | 2026-10-08 | 2026-10-23
134 | 5.51 | Procurement Complete Milestone | 0 | 88, 93, 98, 103, 108, 113, 118, 123, 125, 126 |  | 341 | 341 | 593 | 593 | 252 | 252 | NO | 2027-04-17 | 2027-04-17 | [11 empty] | ◆
135 | 6.1 | B1 Site Mobilization | 5 | 31, 123 | 136, 214, 220, 226, 232, 234, 236, 237 | 241 | 246 | 241 | 246 | 0 | 0 | YES | 2027-01-07 | 2027-01-12
136 | 6.2 | B1 Site Clearing & Demolition | 8 | 135 | 137 | 246 | 254 | 246 | 254 | 0 | 0 | YES | 2027-01-12 | 2027-01-20
137 | 6.3 | B1 Earthworks & Grading | 15 | 136 | 138, 139, 140 | 254 | 269 | 254 | 269 | 0 | 0 | YES | 2027-01-20 | 2027-02-04
138 | 6.4 | B1 Underground Utilities | 25 | 137, 57 | 141 | 269 | 294 | 269 | 294 | 0 | 0 | YES | 2027-02-04 | 2027-03-01
139 | 6.5 | B1 Stormwater Systems | 15 | 137, 48 | 141 | 269 | 284 | 279 | 294 | 10 | 10 | NO | 2027-02-04 | 2027-02-19
140 | 6.6 | B1 Roadways & Parking | 15 | 137 |  | 269 | 284 | 578 | 593 | 309 | 309 | NO | 2027-02-04 | 2027-02-19
141 | 6.7 | B1 Foundation Excavation | 10 | 138, 139, 55 | 142 | 294 | 304 | 294 | 304 | 0 | 0 | YES | 2027-03-01 | 2027-03-11
142 | 6.8 | B1 Foundation Pour | 10 | 141 | 143 | 304 | 314 | 304 | 314 | 0 | 0 | YES | 2027-03-11 | 2027-03-21
143 | 6.9 | B1 Slab on Grade | 15 | 142 | 144, 149, 150, 151, 152, 168, 178, 188, 198 | 314 | 329 | 314 | 329 | 0 | 0 | YES | 2027-03-21 | 2027-04-05
144 | 6.10 | B1 Structural Steel Erection | 35 | 143, 56 | 145, 153 | 329 | 364 | 329 | 364 | 0 | 0 | YES | 2027-04-05 | 2027-05-10
145 | 6.11 | B1 Metal Deck & Concrete Topping | 15 | 144 | 146, 163 | 364 | 379 | 364 | 379 | 0 | 0 | YES | 2027-05-10 | 2027-05-25
146 | 6.12 | B1 Building Envelope | 35 | 145 | 147, 148, 166 | 379 | 414 | 543 | 578 | 164 | 0 | NO | 2027-05-25 | 2027-06-29
147 | 6.13 | B1 Roofing | 15 | 146 |  | 414 | 429 | 578 | 593 | 164 | 164 | NO | 2027-06-29 | 2027-07-14
148 | 6.14 | B1 Loading Docks | 10 | 146 |  | 414 | 424 | 583 | 593 | 169 | 169 | NO | 2027-06-29 | 2027-07-09
149 | 6.15 | B1 Electrical Room Build-out | 15 | 143, 65 | 156, 157, 159 | 329 | 344 | 410 | 425 | 81 | 0 | NO | 2027-04-05 | 2027-04-20
150 | 6.16 | B1 CRAC Gallery Construction | 15 | 143, 59 | 161, 162 | 329 | 344 | 410 | 425 | 81 | 0 | NO | 2027-04-05 | 2027-04-20
151 | 6.17 | B1 Mechanical Room Construction | 15 | 143, 59 | 160 | 329 | 344 | 554 | 569 | 225 | 0 | NO | 2027-04-05 | 2027-04-20
152 | 6.18 | B1 ANR Room Construction | 10 | 143, 74 | 167 | 329 | 339 | 430 | 440 | 101 | 0 | NO | 2027-04-05 | 2027-04-15
153 | 6.19 | B1 MEP Rough-in | 35 | 144, 62, 63 | 154, 155, 165 | 364 | 399 | 410 | 445 | 46 | 0 | NO | 2027-05-10 | 2027-06-14
154 | 6.20 | B1 Fire Suppression Install | 20 | 153, 63 |  | 399 | 419 | 573 | 593 | 174 | 174 | NO | 2027-06-14 | 2027-07-04
155 | 6.21 | B1 Leak Detection Install | 10 | 153, 60 |  | 399 | 409 | 583 | 593 | 184 | 184 | NO | 2027-06-14 | 2027-06-24
156 | 6.22 | B1 Generator Install | 15 | 149, 88 |  | 344 | 359 | 578 | 593 | 234 | 234 | NO | 2027-04-20 | 2027-05-05
157 | 6.23 | B1 Switchgear Install | 15 | 149, 98 | 158, 170, 180, 190, 200 | 344 | 359 | 425 | 440 | 81 | 0 | NO | 2027-04-20 | 2027-05-05
158 | 6.24 | B1 Transformer Install | 10 | 157, 65 |  | 359 | 369 | 583 | 593 | 224 | 224 | NO | 2027-05-05 | 2027-05-15
159 | 6.25 | B1 UPS Install | 10 | 149, 103 |  | 344 | 354 | 583 | 593 | 239 | 239 | NO | 2027-04-20 | 2027-04-30
160 | 6.26 | B1 Chiller Plant Install | 24 | 151, 93 |  | 344 | 368 | 569 | 593 | 225 | 225 | NO | 2027-04-20 | 2027-05-14
161 | 6.27 | B1 CDU Install | 15 | 150, 113 | 171, 181, 191, 201 | 344 | 359 | 425 | 440 | 81 | 81 | NO | 2027-04-20 | 2027-05-05
162 | 6.28 | B1 CRAH/FWU Install | 15 | 150, 118 |  | 344 | 359 | 578 | 593 | 234 | 234 | NO | 2027-04-20 | 2027-05-05
163 | 6.29 | B1 Busduct/HAC Module Install | 30 | 145, 108 | 164, 169, 179, 189, 199 | 379 | 409 | 379 | 409 | 0 | 0 | YES | 2027-05-25 | 2027-06-24
164 | 6.30 | B1 Rack & Cable Tray Install | 15 | 163, 130, 132 | 168, 172, 178, 182, 188, 192, 198, 202 | 409 | 424 | 409 | 424 | 0 | 0 | YES | 2027-06-24 | 2027-07-09
165 | 6.31 | B1 BMS/EPMS/SCADA Install | 15 | 153, 70 | 174, 184, 194, 204 | 399 | 414 | 445 | 460 | 46 | 46 | NO | 2027-06-14 | 2027-06-29
166 | 6.32 | B1 Security Systems Install | 15 | 146, 72, 73 |  | 414 | 429 | 578 | 593 | 164 | 164 | NO | 2027-06-29 | 2027-07-14
167 | 6.33 | B1 Fiber Backbone Install | 10 | 152, 133 | 173, 183, 193, 203 | 339 | 349 | 440 | 450 | 101 | 101 | NO | 2027-04-15 | 2027-04-25
168 | 6.34 | B1 DH1 Floor Sealing & Finishes | 4 | 143, 164 | 169 | 424 | 428 | 424 | 428 | 0 | 0 | YES | 2027-07-09 | 2027-07-13
169 | 6.35 | B1 DH1 HAC Containment | 12 | 168, 163 | 170, 171 | 428 | 440 | 428 | 440 | 0 | 0 | YES | 2027-07-13 | 2027-07-25
170 | 6.36 | B1 DH1 Power Whip & Bus Plug | 6 | 169, 157 | 172 | 440 | 446 | 440 | 446 | 0 | 0 | YES | 2027-07-25 | 2027-07-31
171 | 6.37 | B1 DH1 Cooling Hose & Manifold | 6 | 169, 161 | 172 | 440 | 446 | 440 | 446 | 0 | 0 | YES | 2027-07-25 | 2027-07-31
172 | 6.38 | B1 DH1 Rack Positioning | 4 | 170, 171, 164 | 173 | 446 | 450 | 446 | 450 | 0 | 0 | YES | 2027-07-31 | 2027-08-04
173 | 6.39 | B1 DH1 Network Cabling | 10 | 172, 167 | 174 | 450 | 460 | 450 | 460 | 0 | 0 | YES | 2027-08-04 | 2027-08-14
174 | 6.40 | B1 DH1 Pre-Commissioning | 8 | 173, 165 | 175 | 460 | 468 | 460 | 468 | 0 | 0 | YES | 2027-08-14 | 2027-08-22
175 | 6.41 | B1 DH1 Integrated Systems Test | 10 | 174 | 176 | 468 | 478 | 468 | 478 | 0 | 0 | YES | 2027-08-22 | 2027-09-01
176 | 6.42 | B1 DH1 Performance Verification | 5 | 175 | 177 | 478 | 483 | 478 | 483 | 0 | 0 | YES | 2027-09-01 | 2027-09-06
177 | 6.43 | B1 DH1 RFS Milestone | 0 | 176 | 208 | 483 | 483 | 483 | 483 | 0 | 0 | YES | 2027-09-06 | 2027-09-06 | [16 empty] | ◆
178 | 6.44 | B1 DH2 Floor Sealing & Finishes | 4 | 143, 164 | 179 | 424 | 428 | 446 | 450 | 22 | 0 | NO | 2027-07-09 | 2027-07-13
179 | 6.45 | B1 DH2 HAC Containment | 12 | 178, 163 | 180, 181 | 428 | 440 | 450 | 462 | 22 | 0 | NO | 2027-07-13 | 2027-07-25
180 | 6.46 | B1 DH2 Power Whip & Bus Plug | 6 | 179, 157 | 182 | 440 | 446 | 462 | 468 | 22 | 0 | NO | 2027-07-25 | 2027-07-31
181 | 6.47 | B1 DH2 Cooling Hose & Manifold | 6 | 179, 161 | 182 | 440 | 446 | 462 | 468 | 22 | 0 | NO | 2027-07-25 | 2027-07-31
182 | 6.48 | B1 DH2 Rack Positioning | 4 | 180, 181, 164 | 183 | 446 | 450 | 468 | 472 | 22 | 0 | NO | 2027-07-31 | 2027-08-04
183 | 6.49 | B1 DH2 Network Cabling | 10 | 182, 167 | 184 | 450 | 460 | 472 | 482 | 22 | 0 | NO | 2027-08-04 | 2027-08-14
184 | 6.50 | B1 DH2 Pre-Commissioning | 8 | 183, 165 | 185 | 460 | 468 | 482 | 490 | 22 | 0 | NO | 2027-08-14 | 2027-08-22
185 | 6.51 | B1 DH2 Integrated Systems Test | 10 | 184 | 186 | 468 | 478 | 490 | 500 | 22 | 0 | NO | 2027-08-22 | 2027-09-01
186 | 6.52 | B1 DH2 Performance Verification | 5 | 185 | 187 | 478 | 483 | 500 | 505 | 22 | 0 | NO | 2027-09-01 | 2027-09-06
187 | 6.53 | B1 DH2 RFS Milestone | 0 | 186 | 209 | 483 | 483 | 505 | 505 | 22 | 22 | NO | 2027-09-06 | 2027-09-06 | [16 empty] | ◆
188 | 6.54 | B1 DH3 Floor Sealing & Finishes | 4 | 143, 164 | 189 | 424 | 428 | 468 | 472 | 44 | 0 | NO | 2027-07-09 | 2027-07-13
189 | 6.55 | B1 DH3 HAC Containment | 12 | 188, 163 | 190, 191 | 428 | 440 | 472 | 484 | 44 | 0 | NO | 2027-07-13 | 2027-07-25
190 | 6.56 | B1 DH3 Power Whip & Bus Plug | 6 | 189, 157 | 192 | 440 | 446 | 484 | 490 | 44 | 0 | NO | 2027-07-25 | 2027-07-31
191 | 6.57 | B1 DH3 Cooling Hose & Manifold | 6 | 189, 161 | 192 | 440 | 446 | 484 | 490 | 44 | 0 | NO | 2027-07-25 | 2027-07-31
192 | 6.58 | B1 DH3 Rack Positioning | 4 | 190, 191, 164 | 193 | 446 | 450 | 490 | 494 | 44 | 0 | NO | 2027-07-31 | 2027-08-04
193 | 6.59 | B1 DH3 Network Cabling | 10 | 192, 167 | 194 | 450 | 460 | 494 | 504 | 44 | 0 | NO | 2027-08-04 | 2027-08-14
194 | 6.60 | B1 DH3 Pre-Commissioning | 8 | 193, 165 | 195 | 460 | 468 | 504 | 512 | 44 | 0 | NO | 2027-08-14 | 2027-08-22
195 | 6.61 | B1 DH3 Integrated Systems Test | 10 | 194 | 196 | 468 | 478 | 512 | 522 | 44 | 0 | NO | 2027-08-22 | 2027-09-01
196 | 6.62 | B1 DH3 Performance Verification | 5 | 195 | 197 | 478 | 483 | 522 | 527 | 44 | 0 | NO | 2027-09-01 | 2027-09-06
197 | 6.63 | B1 DH3 RFS Milestone | 0 | 196 | 210 | 483 | 483 | 527 | 527 | 44 | 44 | NO | 2027-09-06 | 2027-09-06 | [16 empty] | ◆
198 | 6.64 | B1 DH4 Floor Sealing & Finishes | 4 | 143, 164 | 199 | 424 | 428 | 490 | 494 | 66 | 0 | NO | 2027-07-09 | 2027-07-13
199 | 6.65 | B1 DH4 HAC Containment | 12 | 198, 163 | 200, 201 | 428 | 440 | 494 | 506 | 66 | 0 | NO | 2027-07-13 | 2027-07-25
200 | 6.66 | B1 DH4 Power Whip & Bus Plug | 6 | 199, 157 | 202 | 440 | 446 | 506 | 512 | 66 | 0 | NO | 2027-07-25 | 2027-07-31
201 | 6.67 | B1 DH4 Cooling Hose & Manifold | 6 | 199, 161 | 202 | 440 | 446 | 506 | 512 | 66 | 0 | NO | 2027-07-25 | 2027-07-31
202 | 6.68 | B1 DH4 Rack Positioning | 4 | 200, 201, 164 | 203 | 446 | 450 | 512 | 516 | 66 | 0 | NO | 2027-07-31 | 2027-08-04
203 | 6.69 | B1 DH4 Network Cabling | 10 | 202, 167 | 204 | 450 | 460 | 516 | 526 | 66 | 0 | NO | 2027-08-04 | 2027-08-14
204 | 6.70 | B1 DH4 Pre-Commissioning | 8 | 203, 165 | 205 | 460 | 468 | 526 | 534 | 66 | 0 | NO | 2027-08-14 | 2027-08-22
205 | 6.71 | B1 DH4 Integrated Systems Test | 10 | 204 | 206 | 468 | 478 | 534 | 544 | 66 | 0 | NO | 2027-08-22 | 2027-09-01
206 | 6.72 | B1 DH4 Performance Verification | 5 | 205 | 207 | 478 | 483 | 544 | 549 | 66 | 0 | NO | 2027-09-01 | 2027-09-06
207 | 6.73 | B1 DH4 RFS Milestone | 0 | 206 | 211 | 483 | 483 | 549 | 549 | 66 | 66 | NO | 2027-09-06 | 2027-09-06 | [16 empty] | ◆
208 | 6.74 | B1 L1-L2 Commissioning (Cold/Dry) | 22 | 177 | 209 | 483 | 505 | 483 | 505 | 0 | 0 | YES | 2027-09-06 | 2027-09-28
209 | 6.75 | B1 L3-L4 Commissioning (Wet/Hot) | 22 | 208, 187 | 210 | 505 | 527 | 505 | 527 | 0 | 0 | YES | 2027-09-28 | 2027-10-20
210 | 6.76 | B1 L5 Commissioning (Integrated) | 22 | 209, 197 | 211 | 527 | 549 | 527 | 549 | 0 | 0 | YES | 2027-10-20 | 2027-11-11
211 | 6.77 | B1 Integrated Building Test | 10 | 210, 207 | 212 | 549 | 559 | 549 | 559 | 0 | 0 | YES | 2027-11-11 | 2027-11-21
212 | 6.78 | B1 Final Acceptance | 6 | 211 | 213 | 559 | 565 | 559 | 565 | 0 | 0 | YES | 2027-11-21 | 2027-11-27
213 | 6.79 | B1 Building Complete Milestone | 0 | 212 | 242 | 565 | 565 | 565 | 565 | 0 | 0 | YES | 2027-11-27 | 2027-11-27 | [18 empty] | ◆
214 | 7.1 | B2 Site Civil & Underground | 25 | 135 | 215 | 246 | 271 | 340 | 365 | 94 | 0 | NO | 2027-01-12 | 2027-02-06
215 | 7.2 | B2 Shell & Core Construction | 60 | 214 | 216 | 271 | 331 | 365 | 425 | 94 | 0 | NO | 2027-02-06 | 2027-04-07
216 | 7.3 | B2 MEP & Equipment Install | 40 | 215 | 217 | 331 | 371 | 425 | 465 | 94 | 0 | NO | 2027-04-07 | 2027-05-17
217 | 7.4 | B2 Data Halls Fit-out | 60 | 216 | 218 | 371 | 431 | 465 | 525 | 94 | 0 | NO | 2027-05-17 | 2027-07-16
218 | 7.5 | B2 Commissioning & RFS | 40 | 217 | 219 | 431 | 471 | 525 | 565 | 94 | 0 | NO | 2027-07-16 | 2027-08-25
219 | 7.6 | B2 Building Complete | 0 | 218 | 242 | 471 | 471 | 565 | 565 | 94 | 94 | NO | 2027-08-25 | 2027-08-25 | [15 empty] | ◆
220 | 8.1 | B3 Site Civil & Underground | 25 | 135 | 221 | 246 | 271 | 340 | 365 | 94 | 0 | NO | 2027-01-12 | 2027-02-06
221 | 8.2 | B3 Shell & Core Construction | 60 | 220 | 222 | 271 | 331 | 365 | 425 | 94 | 0 | NO | 2027-02-06 | 2027-04-07
222 | 8.3 | B3 MEP & Equipment Install | 40 | 221 | 223 | 331 | 371 | 425 | 465 | 94 | 0 | NO | 2027-04-07 | 2027-05-17
223 | 8.4 | B3 Data Halls Fit-out | 60 | 222 | 224 | 371 | 431 | 465 | 525 | 94 | 0 | NO | 2027-05-17 | 2027-07-16
224 | 8.5 | B3 Commissioning & RFS | 40 | 223 | 225 | 431 | 471 | 525 | 565 | 94 | 0 | NO | 2027-07-16 | 2027-08-25
225 | 8.6 | B3 Building Complete | 0 | 224 | 242 | 471 | 471 | 565 | 565 | 94 | 94 | NO | 2027-08-25 | 2027-08-25 | [15 empty] | ◆
226 | 9.1 | B4 Site Civil & Underground | 25 | 135 | 227 | 246 | 271 | 340 | 365 | 94 | 0 | NO | 2027-01-12 | 2027-02-06
227 | 9.2 | B4 Shell & Core Construction | 60 | 226 | 228 | 271 | 331 | 365 | 425 | 94 | 0 | NO | 2027-02-06 | 2027-04-07
228 | 9.3 | B4 MEP & Equipment Install | 40 | 227 | 229 | 331 | 371 | 425 | 465 | 94 | 0 | NO | 2027-04-07 | 2027-05-17
229 | 9.4 | B4 Data Halls Fit-out | 60 | 228 | 230 | 371 | 431 | 465 | 525 | 94 | 0 | NO | 2027-05-17 | 2027-07-16
230 | 9.5 | B4 Commissioning & RFS | 40 | 229 | 231 | 431 | 471 | 525 | 565 | 94 | 0 | NO | 2027-07-16 | 2027-08-25
231 | 9.6 | B4 Building Complete | 0 | 230 | 242 | 471 | 471 | 565 | 565 | 94 | 94 | NO | 2027-08-25 | 2027-08-25 | [15 empty] | ◆
232 | 10.1 | Campus Roadways & Fencing | 35 | 135 | 233 | 246 | 281 | 505 | 540 | 259 | 0 | NO | 2027-01-12 | 2027-02-16
233 | 10.2 | Campus Security Gates & Perimeter | 25 | 232, 71 | 235, 239 | 281 | 306 | 540 | 565 | 259 | 0 | NO | 2027-02-16 | 2027-03-13
234 | 10.3 | Campus Substation Construction | 60 | 135, 38 | 240 | 246 | 306 | 515 | 575 | 269 | 0 | NO | 2027-01-12 | 2027-03-13
235 | 10.4 | Campus Fiber Entry Points (4) | 15 | 233, 75 | 241 | 306 | 321 | 575 | 590 | 269 | 10 | NO | 2027-03-13 | 2027-03-28
236 | 10.5 | Campus Admin Building | 60 | 135, 46 | 238, 239 | 246 | 306 | 505 | 565 | 259 | 0 | NO | 2027-01-12 | 2027-03-13
237 | 10.6 | Campus Loading Docks (6 total) | 28 | 135, 46 | 241 | 246 | 274 | 562 | 590 | 316 | 57 | NO | 2027-01-12 | 2027-02-09
238 | 10.7 | Campus Pharmacy & Storage | 15 | 236 | 241 | 306 | 321 | 575 | 590 | 269 | 10 | NO | 2027-03-13 | 2027-03-28
239 | 10.8 | Campus Security SOC/FOC/MDF | 25 | 236, 233 | 241 | 306 | 331 | 565 | 590 | 259 | 0 | NO | 2027-03-13 | 2027-04-07
240 | 10.9 | Campus Utility Yard | 15 | 234 | 241 | 306 | 321 | 575 | 590 | 269 | 10 | NO | 2027-03-13 | 2027-03-28
241 | 10.10 | Campus Infrastructure Complete | 0 | 235, 237, 238, 239, 240 | 245 | 331 | 331 | 590 | 590 | 259 | 259 | NO | 2027-04-07 | 2027-04-07 | [11 empty] | ◆
242 | 11.1 | As-Built Documentation | 10 | 213, 219, 225, 231 | 243 | 565 | 575 | 565 | 575 | 0 | 0 | YES | 2027-11-27 | 2027-12-07
243 | 11.2 | O&M Manuals & Training | 10 | 242 | 244 | 575 | 585 | 575 | 585 | 0 | 0 | YES | 2027-12-07 | 2027-12-17
244 | 11.3 | Warranty & Guarantee Handover | 5 | 243 | 245 | 585 | 590 | 585 | 590 | 0 | 0 | YES | 2027-12-17 | 2027-12-22
245 | 11.4 | Final Project Acceptance | 3 | 244, 241 | 246 | 590 | 593 | 590 | 593 | 0 | 0 | YES | 2027-12-22 | 2027-12-25
246 | 11.5 | 1 GW Campus RFS Milestone | 0 | 245 |  | 593 | 593 | 593 | 593 | 0 | 0 | YES | 2027-12-25 | 2027-12-25 | [19 empty] | ◆

## Critical Path
ID | WBS | Activity Name | Duration | ES | EF | LS | LF | Total Float | Start Date | Finish Date | Resources
1 | 1.1 | Project Kick-off & Charter | 5 | 0 | 5 | 0 | 5 | 0 | 2026-05-11 | 2026-05-16 | PM(8), Admin(2)
7 | 2.1 | Term Sheet Negotiation | 12 | 5 | 17 | 5 | 17 | 0 | 2026-05-16 | 2026-05-28 | Legal(4), BD(3), PM(2)
8 | 2.2 | Definitive Agreement Drafting | 15 | 17 | 32 | 17 | 32 | 0 | 2026-05-28 | 2026-06-12 | Legal(5), BD(2)
9 | 2.3 | Legal Review & Revisions | 10 | 32 | 42 | 32 | 42 | 0 | 2026-06-12 | 2026-06-22 | Legal(4), PM(2)
15 | 2.9 | Debt Financing Arrangement | 28 | 42 | 70 | 42 | 70 | 0 | 2026-06-22 | 2026-07-20 | Finance(5), Legal(3)
17 | 2.11 | Financial Close Milestone | 0 | 70 | 70 | 70 | 70 | 0 | 2026-07-20 | 2026-07-20 | PM(2), Exec(2)
46 | 4.1 | Campus Master Plan | 20 | 70 | 90 | 70 | 90 | 0 | 2026-07-20 | 2026-08-09 | Arch(5), Civil(3), MEP(2)
49 | 4.4 | Concept Design | 15 | 90 | 105 | 90 | 105 | 0 | 2026-08-09 | 2026-08-24 | Arch(6), MEP(2), Struct(2)
50 | 4.5 | Schematic Design | 20 | 105 | 125 | 105 | 125 | 0 | 2026-08-24 | 2026-09-13 | Arch(8), MEP(4), Struct(3), Elect(3)
51 | 4.6 | Design Development | 25 | 125 | 150 | 125 | 150 | 0 | 2026-09-13 | 2026-10-08 | Arch(8), MEP(5), Struct(4), Elect(4), Security(2)
52 | 4.7 | Construction Documents | 40 | 150 | 190 | 150 | 190 | 0 | 2026-10-08 | 2026-11-17 | Arch(10), MEP(6), Struct(5), Elect(5), Security(2)
119 | 5.36 | GC Prequalification | 12 | 190 | 202 | 190 | 202 | 0 | 2026-11-17 | 2026-11-29 | PM(2), Procure(3), Legal(1)
120 | 5.37 | GC RFP Issue | 12 | 202 | 214 | 202 | 214 | 0 | 2026-11-29 | 2026-12-11 | PM(2), Procure(2), Legal(1)
121 | 5.38 | GC Bid Evaluation | 12 | 214 | 226 | 214 | 226 | 0 | 2026-12-11 | 2026-12-23 | PM(3), Procure(3), Cost(2)
122 | 5.39 | GC Contract Negotiation | 12 | 226 | 238 | 226 | 238 | 0 | 2026-12-23 | 2027-01-04 | PM(3), Legal(3), Procure(2)
123 | 5.40 | GC Contract Award | 3 | 238 | 241 | 238 | 241 | 0 | 2027-01-04 | 2027-01-07 | PM(2), Legal(1), Exec(1)
135 | 6.1 | B1 Site Mobilization | 5 | 241 | 246 | 241 | 246 | 0 | 2027-01-07 | 2027-01-12 | GC(5), PM(2), Safety(2)
136 | 6.2 | B1 Site Clearing & Demolition | 8 | 246 | 254 | 246 | 254 | 0 | 2027-01-12 | 2027-01-20 | GC(8), Labor(20), Equip(5)
137 | 6.3 | B1 Earthworks & Grading | 15 | 254 | 269 | 254 | 269 | 0 | 2027-01-20 | 2027-02-04 | GC(5), Labor(25), Equip(8), Civil(3)
138 | 6.4 | B1 Underground Utilities | 25 | 269 | 294 | 269 | 294 | 0 | 2027-02-04 | 2027-03-01 | GC(5), Labor(30), MEP(5), Civil(3)
141 | 6.7 | B1 Foundation Excavation | 10 | 294 | 304 | 294 | 304 | 0 | 2027-03-01 | 2027-03-11 | GC(5), Labor(25), Equip(6), Struct(2)
142 | 6.8 | B1 Foundation Pour | 10 | 304 | 314 | 304 | 314 | 0 | 2027-03-11 | 2027-03-21 | GC(5), Labor(30), Concrete(15), Struct(3)
143 | 6.9 | B1 Slab on Grade | 15 | 314 | 329 | 314 | 329 | 0 | 2027-03-21 | 2027-04-05 | GC(5), Labor(35), Concrete(20), Struct(3)
144 | 6.10 | B1 Structural Steel Erection | 35 | 329 | 364 | 329 | 364 | 0 | 2027-04-05 | 2027-05-10 | GC(6), Labor(40), Steel(15), Equip(10), Struct(3)
145 | 6.11 | B1 Metal Deck & Concrete Topping | 15 | 364 | 379 | 364 | 379 | 0 | 2027-05-10 | 2027-05-25 | GC(5), Labor(30), Concrete(15), Steel(5)
163 | 6.29 | B1 Busduct/HAC Module Install | 30 | 379 | 409 | 379 | 409 | 0 | 2027-05-25 | 2027-06-24 | GC(5), Labor(25), Elect(8), MEP(5), Vendor(3)
164 | 6.30 | B1 Rack & Cable Tray Install | 15 | 409 | 424 | 409 | 424 | 0 | 2027-06-24 | 2027-07-09 | GC(4), Labor(20), IT(5), Elect(4), MEP(3)
168 | 6.34 | B1 DH1 Floor Sealing & Finishes | 4 | 424 | 428 | 424 | 428 | 0 | 2027-07-09 | 2027-07-13 | GC(3), Labor(15), Floor(5)
169 | 6.35 | B1 DH1 HAC Containment | 12 | 428 | 440 | 428 | 440 | 0 | 2027-07-13 | 2027-07-25 | GC(4), Labor(20), MEP(5), Elect(3)
170 | 6.36 | B1 DH1 Power Whip & Bus Plug | 6 | 440 | 446 | 440 | 446 | 0 | 2027-07-25 | 2027-07-31 | GC(3), Labor(15), Elect(6), MEP(2)
171 | 6.37 | B1 DH1 Cooling Hose & Manifold | 6 | 440 | 446 | 440 | 446 | 0 | 2027-07-25 | 2027-07-31 | GC(3), Labor(15), MEP(6), Mech(3)
172 | 6.38 | B1 DH1 Rack Positioning | 4 | 446 | 450 | 446 | 450 | 0 | 2027-07-31 | 2027-08-04 | GC(3), Labor(12), IT(5), Elect(2)
173 | 6.39 | B1 DH1 Network Cabling | 10 | 450 | 460 | 450 | 460 | 0 | 2027-08-04 | 2027-08-14 | GC(3), Labor(15), IT(8), Elect(3)
174 | 6.40 | B1 DH1 Pre-Commissioning | 8 | 460 | 468 | 460 | 468 | 0 | 2027-08-14 | 2027-08-22 | GC(3), Labor(10), MEP(4), Elect(3), Controls(3)
175 | 6.41 | B1 DH1 Integrated Systems Test | 10 | 468 | 478 | 468 | 478 | 0 | 2027-08-22 | 2027-09-01 | GC(3), Labor(12), MEP(5), Elect(4), IT(4), Controls(3)
176 | 6.42 | B1 DH1 Performance Verification | 5 | 478 | 483 | 478 | 483 | 0 | 2027-09-01 | 2027-09-06 | GC(2), Labor(8), MEP(3), Elect(2), IT(3), Client(2)
177 | 6.43 | B1 DH1 RFS Milestone | 0 | 483 | 483 | 483 | 483 | 0 | 2027-09-06 | 2027-09-06 | PM(2), Client(3), Exec(1)
208 | 6.74 | B1 L1-L2 Commissioning (Cold/Dry) | 22 | 483 | 505 | 483 | 505 | 0 | 2027-09-06 | 2027-09-28 | Commission(8), MEP(4), Elect(4), Controls(4)
209 | 6.75 | B1 L3-L4 Commissioning (Wet/Hot) | 22 | 505 | 527 | 505 | 527 | 0 | 2027-09-28 | 2027-10-20 | Commission(8), MEP(5), Elect(4), Controls(4), IT(3)
210 | 6.76 | B1 L5 Commissioning (Integrated) | 22 | 527 | 549 | 527 | 549 | 0 | 2027-10-20 | 2027-11-11 | Commission(10), MEP(6), Elect(5), Controls(5), IT(5), Client(3)
211 | 6.77 | B1 Integrated Building Test | 10 | 549 | 559 | 549 | 559 | 0 | 2027-11-11 | 2027-11-21 | Commission(6), MEP(4), Elect(4), Controls(4), IT(3), Client(2)
212 | 6.78 | B1 Final Acceptance | 6 | 559 | 565 | 559 | 565 | 0 | 2027-11-21 | 2027-11-27 | PM(3), Client(3), Exec(2), Commission(4)
213 | 6.79 | B1 Building Complete Milestone | 0 | 565 | 565 | 565 | 565 | 0 | 2027-11-27 | 2027-11-27 | PM(2), Exec(1), Client(2)
242 | 11.1 | As-Built Documentation | 10 | 565 | 575 | 565 | 575 | 0 | 2027-11-27 | 2027-12-07 | PM(3), Arch(2), MEP(2), Elect(2)
243 | 11.2 | O&M Manuals & Training | 10 | 575 | 585 | 575 | 585 | 0 | 2027-12-07 | 2027-12-17 | PM(3), MEP(3), Elect(3), Controls(2), IT(2)
244 | 11.3 | Warranty & Guarantee Handover | 5 | 585 | 590 | 585 | 590 | 0 | 2027-12-17 | 2027-12-22 | PM(2), Legal(1), Exec(1)
245 | 11.4 | Final Project Acceptance | 3 | 590 | 593 | 590 | 593 | 0 | 2027-12-22 | 2027-12-25 | PM(3), Exec(2), Client(3)
246 | 11.5 | 1 GW Campus RFS Milestone | 0 | 593 | 593 | 593 | 593 | 0 | 2027-12-25 | 2027-12-25 | PM(2), Exec(2), Client(5)

## Manpower Histogram
Week # | Week Start | Week End | Labor | MEP | Elect | IT | Commission | GC | PM | Controls | Security | Total
1 | 2026-05-11 | 2026-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 3 | 24
2 | 2026-05-18 | 2026-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 3 | 24
3 | 2026-05-25 | 2026-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 3 | 18
4 | 2026-06-01 | 2026-06-07 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
5 | 2026-06-08 | 2026-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 11
6 | 2026-06-15 | 2026-06-21 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7
7 | 2026-06-22 | 2026-06-28 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
8 | 2026-06-29 | 2026-07-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2026-07-06 | 2026-07-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2026-07-13 | 2026-07-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 2026-07-20 | 2026-07-26 | 0 | 2 | 3 | 0 | 0 | 0 | 13 | 0 | 0 | 18
12 | 2026-07-27 | 2026-08-02 | 0 | 2 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 18
13 | 2026-08-03 | 2026-08-09 | 0 | 4 | 5 | 0 | 0 | 0 | 7 | 0 | 0 | 16
14 | 2026-08-10 | 2026-08-16 | 0 | 2 | 5 | 0 | 0 | 0 | 7 | 0 | 0 | 14
15 | 2026-08-17 | 2026-08-23 | 0 | 2 | 3 | 0 | 0 | 0 | 7 | 0 | 0 | 12
16 | 2026-08-24 | 2026-08-30 | 0 | 8 | 12 | 0 | 0 | 0 | 13 | 0 | 0 | 33
17 | 2026-08-31 | 2026-09-06 | 0 | 4 | 7 | 0 | 0 | 0 | 6 | 0 | 0 | 17
18 | 2026-09-07 | 2026-09-13 | 0 | 20 | 19 | 4 | 0 | 0 | 8 | 0 | 2 | 53
19 | 2026-09-14 | 2026-09-20 | 0 | 16 | 16 | 4 | 0 | 0 | 4 | 0 | 2 | 42
20 | 2026-09-21 | 2026-09-27 | 0 | 14 | 14 | 4 | 0 | 0 | 2 | 0 | 2 | 36
21 | 2026-09-28 | 2026-10-04 | 0 | 33 | 30 | 11 | 0 | 0 | 4 | 0 | 2 | 80
22 | 2026-10-05 | 2026-10-11 | 0 | 44 | 40 | 11 | 0 | 0 | 6 | 5 | 8 | 114
23 | 2026-10-12 | 2026-10-18 | 0 | 45 | 40 | 8 | 0 | 0 | 2 | 5 | 6 | 106
24 | 2026-10-19 | 2026-10-25 | 0 | 26 | 28 | 4 | 0 | 0 | 2 | 5 | 6 | 71
25 | 2026-10-26 | 2026-11-01 | 0 | 30 | 38 | 4 | 0 | 0 | 6 | 5 | 12 | 95
26 | 2026-11-02 | 2026-11-08 | 0 | 21 | 26 | 4 | 0 | 0 | 8 | 5 | 8 | 72
27 | 2026-11-09 | 2026-11-15 | 0 | 12 | 13 | 0 | 0 | 0 | 4 | 0 | 5 | 34
28 | 2026-11-16 | 2026-11-22 | 0 | 17 | 12 | 0 | 0 | 0 | 10 | 0 | 2 | 41
29 | 2026-11-23 | 2026-11-29 | 0 | 7 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 15
30 | 2026-11-30 | 2026-12-06 | 0 | 7 | 3 | 0 | 0 | 0 | 8 | 0 | 0 | 18
31 | 2026-12-07 | 2026-12-13 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5
32 | 2026-12-14 | 2026-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
33 | 2026-12-21 | 2026-12-27 | 0 | 2 | 0 | 0 | 0 | 0 | 11 | 0 | 2 | 15
34 | 2026-12-28 | 2027-01-03 | 0 | 2 | 0 | 0 | 0 | 0 | 8 | 0 | 2 | 12
35 | 2027-01-04 | 2027-01-10 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 13
36 | 2027-01-11 | 2027-01-17 | 215 | 3 | 10 | 0 | 0 | 45 | 5 | 0 | 0 | 278
37 | 2027-01-18 | 2027-01-24 | 240 | 5 | 12 | 0 | 0 | 45 | 4 | 0 | 0 | 306
38 | 2027-01-25 | 2027-01-31 | 220 | 5 | 12 | 0 | 0 | 37 | 4 | 0 | 0 | 278
39 | 2027-02-01 | 2027-02-07 | 425 | 12 | 12 | 0 | 0 | 68 | 4 | 0 | 0 | 521
40 | 2027-02-08 | 2027-02-14 | 310 | 12 | 10 | 0 | 0 | 48 | 3 | 0 | 0 | 383
41 | 2027-02-15 | 2027-02-21 | 310 | 10 | 11 | 0 | 0 | 48 | 1 | 0 | 5 | 385
42 | 2027-02-22 | 2027-02-28 | 245 | 10 | 11 | 0 | 0 | 36 | 1 | 0 | 5 | 308
43 | 2027-03-01 | 2027-03-07 | 270 | 8 | 11 | 0 | 0 | 41 | 0 | 0 | 5 | 335
44 | 2027-03-08 | 2027-03-14 | 330 | 8 | 17 | 9 | 0 | 53 | 0 | 0 | 10 | 427
45 | 2027-03-15 | 2027-03-21 | 260 | 5 | 6 | 9 | 0 | 40 | 0 | 0 | 5 | 325
46 | 2027-03-22 | 2027-03-28 | 230 | 5 | 8 | 9 | 0 | 35 | 1 | 0 | 5 | 293
47 | 2027-03-29 | 2027-04-04 | 185 | 0 | 5 | 4 | 0 | 26 | 1 | 0 | 5 | 226
48 | 2027-04-05 | 2027-04-11 | 405 | 40 | 30 | 7 | 0 | 63 | 3 | 0 | 5 | 553
49 | 2027-04-12 | 2027-04-18 | 230 | 40 | 29 | 8 | 0 | 40 | 3 | 0 | 0 | 350
50 | 2027-04-19 | 2027-04-25 | 345 | 57 | 51 | 5 | 0 | 63 | 0 | 0 | 0 | 521
51 | 2027-04-26 | 2027-05-02 | 275 | 44 | 44 | 0 | 0 | 48 | 0 | 0 | 0 | 411
52 | 2027-05-03 | 2027-05-09 | 275 | 44 | 44 | 0 | 0 | 48 | 0 | 0 | 0 | 411
53 | 2027-05-10 | 2027-05-16 | 260 | 42 | 34 | 0 | 0 | 40 | 0 | 0 | 0 | 376
54 | 2027-05-17 | 2027-05-23 | 295 | 52 | 41 | 18 | 0 | 40 | 0 | 0 | 0 | 446
55 | 2027-05-24 | 2027-05-30 | 250 | 33 | 31 | 18 | 0 | 35 | 0 | 0 | 0 | 367
56 | 2027-05-31 | 2027-06-06 | 220 | 33 | 31 | 18 | 0 | 30 | 0 | 0 | 0 | 332
57 | 2027-06-07 | 2027-06-13 | 220 | 33 | 31 | 18 | 0 | 30 | 0 | 0 | 0 | 332
58 | 2027-06-14 | 2027-06-20 | 270 | 41 | 35 | 21 | 0 | 41 | 0 | 8 | 0 | 416
59 | 2027-06-21 | 2027-06-27 | 250 | 34 | 31 | 26 | 0 | 40 | 0 | 8 | 0 | 389
60 | 2027-06-28 | 2027-07-04 | 265 | 25 | 26 | 28 | 0 | 44 | 0 | 6 | 6 | 400
61 | 2027-07-05 | 2027-07-11 | 250 | 21 | 22 | 25 | 0 | 43 | 0 | 0 | 6 | 367
62 | 2027-07-12 | 2027-07-18 | 295 | 53 | 42 | 32 | 24 | 51 | 0 | 12 | 6 | 515
63 | 2027-07-19 | 2027-07-25 | 200 | 67 | 48 | 12 | 24 | 40 | 0 | 12 | 0 | 403
64 | 2027-07-26 | 2027-08-01 | 168 | 47 | 44 | 32 | 24 | 36 | 0 | 12 | 0 | 363
65 | 2027-08-02 | 2027-08-08 | 108 | 15 | 32 | 64 | 24 | 24 | 0 | 12 | 0 | 279
66 | 2027-08-09 | 2027-08-15 | 100 | 31 | 36 | 44 | 24 | 24 | 0 | 24 | 0 | 283
67 | 2027-08-16 | 2027-08-22 | 88 | 51 | 40 | 28 | 24 | 24 | 0 | 36 | 0 | 291
68 | 2027-08-23 | 2027-08-29 | 48 | 35 | 28 | 28 | 24 | 12 | 6 | 24 | 0 | 205
69 | 2027-08-30 | 2027-09-05 | 80 | 32 | 24 | 28 | 0 | 20 | 0 | 12 | 0 | 196
70 | 2027-09-06 | 2027-09-12 | 32 | 16 | 12 | 12 | 8 | 8 | 8 | 4 | 0 | 100
71 | 2027-09-13 | 2027-09-19 | 0 | 4 | 4 | 0 | 8 | 0 | 0 | 4 | 0 | 20
72 | 2027-09-20 | 2027-09-26 | 0 | 4 | 4 | 0 | 8 | 0 | 0 | 4 | 0 | 20
73 | 2027-09-27 | 2027-10-03 | 0 | 9 | 8 | 3 | 16 | 0 | 0 | 8 | 0 | 44
74 | 2027-10-04 | 2027-10-10 | 0 | 5 | 4 | 3 | 8 | 0 | 0 | 4 | 0 | 24
75 | 2027-10-11 | 2027-10-17 | 0 | 5 | 4 | 3 | 8 | 0 | 0 | 4 | 0 | 24
76 | 2027-10-18 | 2027-10-24 | 0 | 11 | 9 | 8 | 18 | 0 | 0 | 9 | 0 | 55
77 | 2027-10-25 | 2027-10-31 | 0 | 6 | 5 | 5 | 10 | 0 | 0 | 5 | 0 | 31
78 | 2027-11-01 | 2027-11-07 | 0 | 6 | 5 | 5 | 10 | 0 | 0 | 5 | 0 | 31
79 | 2027-11-08 | 2027-11-14 | 0 | 10 | 9 | 8 | 16 | 0 | 0 | 9 | 0 | 52
80 | 2027-11-15 | 2027-11-21 | 0 | 4 | 4 | 3 | 10 | 0 | 3 | 4 | 0 | 28
81 | 2027-11-22 | 2027-11-28 | 0 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 0 | 16
82 | 2027-11-29 | 2027-12-05 | 0 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 7
83 | 2027-12-06 | 2027-12-12 | 0 | 5 | 5 | 2 | 0 | 0 | 6 | 2 | 0 | 20
84 | 2027-12-13 | 2027-12-19 | 0 | 3 | 3 | 2 | 0 | 0 | 5 | 2 | 0 | 15
85 | 2027-12-20 | 2027-12-26 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7
86 | 2027-12-27 | 2028-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## WBS Dictionary
WBS Code | WBS Element | Description
1.0 | Project Management & Governance | PMO, controls, risk, steering reviews, closeout.
2.0 | Transaction & Financial Close | Agreements, due diligence, equity/debt, insurance.
3.0 | Site Development & Entitlements | Permits, TFO/LDC, Indigenous, community.
4.0 | Design & Engineering | Concept to IFC, structural, MEP, fire, security, BMS.
5.0 | Procurement & Supply Chain | Long-lead equipment, GC/MEP/security awards.
6.0 | Building 1 Construction (240 MW) | Site, shell, MEP, 4 data halls, commissioning, RFS.
7.0 | Building 2 Construction (240 MW) | Civil, shell, MEP, fit-out, commissioning, RFS.
8.0 | Building 3 Construction (240 MW) | Civil, shell, MEP, fit-out, commissioning, RFS.
9.0 | Building 4 Construction (240 MW) | Civil, shell, MEP, fit-out, commissioning, RFS.
10.0 | Campus Infrastructure | Roads, security, substation, fiber, admin, docks.
11.0 | Project Closeout | As-builts, O&M, training, warranty, final acceptance.

## Schedule Analysis
AGGRESSIVE PARALLEL SCHEDULE — 1 GW CAMPUS BY DECEMBER 2027
Schedule Philosophy: All 4 buildings constructed in parallel from Day 1.
L2 Schedule Results:
• Project Duration: 593 days (2026-05-11 to 2027-12-25)
• B1 DH1 RFS: 2027-09-06
• B1 Building Complete: 2027-11-27
• B2 Building Complete: 2027-08-25 (TF=94)
• B3 Building Complete: 2027-08-25 (TF=94)
• B4 Building Complete: 2027-08-25 (TF=94)
• 1 GW Campus RFS: 2027-12-25 — ACHIEVED before Dec 31, 2027
PARALLEL EXECUTION STRATEGY:
1. FOUR BUILDINGS, FOUR CREWS
• B2, B3, B4 civil works start at B1 mobilization (Aug 2026), not after B1 slab.
• Each building has dedicated GC crew + MEP subcontractor.
• Equipment delivery sized for all 4 buildings (not just B1).
2. COMPRESSED BUILDING DURATIONS
• Site Civil: 25 days (was 35) — shared earthworks crew, sequential then parallel.
• Shell & Core: 60 days (was 75) — precast panels instead of cast-in-place where possible.
• MEP Install: 40 days (was 50) — prefabricated MEP racks installed by crane.
• Data Halls Fit-out: 60 days (was 75) — modular HAC units, pre-terminated cabling.
• Commissioning: 40 days (was 50) — parallel commissioning teams per building.
3. FAST-TRACK CLOSEOUT
• As-Built Documentation: 10 days (was 15) — digital twin updated real-time during construction.
• O&M Manuals & Training: 10 days (was 15) — vendor pre-populated templates.
• Warranty Handover: 5 days (was 8).
• Final Acceptance: 3 days (was 5) — Anthropic embedded QA team from Day 1.
CRITICAL PATH (B1-DRIVEN):
• Financial Close → TFO Interconnection → LDC Agreement → B1 Site Works → B1 Shell →
B1 MEP/Equipment → B1 DH1 Fit-out → B1 DH1 Commissioning → B1 Building Complete → Closeout → 1 GW RFS
B2-B4 FLOAT: +94 days
• B2-B4 finish Aug 25, 2027 — 4 months before B1 and 4 months before final RFS.
• This float acts as strategic reserve: if B1 slips, B2-B4 resources can be redeployed to B1.
• If B1 stays on track, B2-B4 float can be used for optimization / early revenue.
MANPOWER PROFILE:
• Peak total manpower: 553 heads (week of 2027-04-05)
• Peak Labor: 425
• Peak MEP: 67
• Peak Elect: 51
• Peak IT: 64
RISK FACTORS:
• Winter construction (Nov-Mar): Heated enclosures + accelerated concrete curing required.
• Equipment supply chain: 4x equipment quantities must be ordered at Financial Close.
• Labor shortage: 553 peak headcount requires pre-negotiated union agreements + second shift.
• TFO interconnection: 40-day System Impact Study is statutory — no compression possible.
• Indigenous consultation: 50-day statutory timeline — commenced at Financial Close.
REALISM CHECK:
• This schedule is aggressive but achievable IF:
(a) Four separate GCs or one mega-GC with 4 independent crews.
(b) Design is 100% complete (IFC) before any B2-B4 shell work starts.
(c) All long-lead equipment POs placed at 30% design review.
(d) Anthropic embeds commissioning team from MEP install phase (not post-fit-out).
(e) Winter work premiums (heated enclosures, concrete additives) budgeted at 15% uplift.