## Change Log_Al Ayuni_DD-2023-118
Contract Ref: DD-2023-118
Contractor : Al Ayuni
[6 empty] | Contractor Proposal |  |  |  | Change Control Form(CCF) | [18 empty] | Variation Order (VO)
[10 empty] | Engineer/PMC Assessment | [14 empty] | Flow of Actions |  |  |  | Engineer/PMC Assessment | [7 empty] | Flow of Actions
Sl. | Contract Ref | Title of Change | Change Driver | Advance Warning Incl. VAT | Date of Notice | Date of Proposal | Cost Incl. VAT | Time Impact | Remarks | CCF Ref: | CCF Date | Activated Provisional Sum (Yes/No) | Engineer Assessment Incl. VAT | PMC Assessment Incl. VAT | Approved CCF Amount Incl. VAT | Time Impact | CCF Status | Action Owner | CCF Initiation Date on Aconex | CCF Approval on Aconex | Workflow Ref: | Engineer Instruction Ref: (If issued) | EI Date | PR Ref: (Shares by DGCL) | Planned Action Date | Forecast/Actual Completion | Due (+ve)/Over Due (-ve) | Remarks | VO Ref | Final VO Amount Incl. VAT | Time Impact | VO Initiation Date on Aconex | VO Approval on Aconex | Workflow Ref: | VO Status | Action Owner | Planned Action Date | Forecast/Actual Completion | Due (+ve)/Over Due (-ve) | Remarks | PO (Ref:4200000705 ) Updates (Yes/N0)
1 | DD-2023-118 | RFC 41 - Diriyah Seasons Requirements | DGCL |  |  | 2023-09-07 |  |  |  | CCF-41 | 2023-10-09 | No | 0 | 0 | 0 | 0 | CCF Approved by DGCL | Closed | 2023-09-10 | 2023-11-05 | WF-008196 | 1. P-LND-061-0000-JCB-LTR-000205 2. IP-LND-061-0000-JCB-LTR-000182 3. IP-LND-061-0000-JCB-LTR-000188 4.IP-LND-061-0000-JCB-LTR-MN-0001296 |  | 70002020 | 2023-09-30 | 2023-11-05 | -36 | 1.Requested addiitonal information from the contractor on 10th Sep 2023 2. Contractor shared the documents on XXXX 3. Engineer assessment shared in PMC on XXXXX 4. PMC shared the draft CCF with DGCL on XXXX | VO Ref: 31 | 4673480.2 | 0 |  | 2024-02-12 | WF-013277 | Closed - VO singned by Contractor | Closed | 2023-11-17 | 2024-02-12 | -87 | 1.Requested addiitonal information from the contractor on 10th Sep 2023 2. Contractor shared the documents on XXXX 3. Engineer assessment shared in PMC on XXXXX 4. PMC shared the draft CCF with DGCL on XXXX | Yes
|  | Total |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | [14 empty] | 4673480.2
Advance Warning
1 | DD-2023-118 | Shifting the stockpiled material to the approved location | Contractor | 7032480 |  | 2024-03-03 | 17904120 | N/A |  | AW 01 | [31 empty] | MOM dated 03/03/2024
2 | DD-2023-118 | Omission of Surveying Equipment (Still on Hold) | Engineer | -232173.5 | [5 empty] | AW 02 | [31 empty] | Engineer's letter ref. IP-INF-054-0000-JCB-LTR-MN-000052 dated 21 April 2024
3 | DD-2023-118 | Omission of insurances | Engineer | -2532319.1247 | [5 empty] | AW 03
4 | DD-2023-118 | Omission of Vehicles | Engineer | -9095745.6 | [5 empty] | AW 04
5 | DD-2023-118 | Omission of Site Laboratory ( Still On Hold) | Engineer | -1165663 | [5 empty] | AW 05
6 | DD-2023-118 | Natural Ground Level at Media Area | Contractor | 0 | [5 empty] | AW 06 | [31 empty] | Contractor's letter ref. IP-054-0000-AIC-LTR-MN-000004 dated 25 Januray 2024
7 | DD-2023-118 | Potential Prolongation Cost due to delay in Access to Site | Contractor | 6795182.3115 | [5 empty] | AW 07
8 | DD-2023-118 | Increase in Fuel Cost (rejected by the Engineer) | Contractor | 23526150.2539 | [5 empty] | AW 08
9 | DD-2023-118 | Parent Company Gurantee | Engineer | -107199.1247 | [5 empty] | AW 09 | [31 empty] | Engineer's letter ref. IP-INF-054-0000-JCB-LTR-MN-000052 dated 21 April 2024
10 | DD-2023-118 | Late Issuance of IFC Drawings (Prolongation) | Contractor | [6 empty] | AW 10
11 | DD-2023-118 | Omission of the attendance upon the Engineer for Chainman and Laboratory Assistant services (On Hold) | Engineer | -1028790 | [5 empty] | AW 11 | [31 empty] | Engineer's letter ref. IP-INF-054-0000-JCB-LTR-MN-000052 dated 21 April 2024
12 | DD-2023-118 | Omission of Retention Bond | Engineer | -2078855.6387 | [5 empty] | AW 12
13 | DD-2023-118 | Omission of Measuring and Recording Equipment (On Hold). | Engineer | -28750 | [5 empty] | AW 13
14 | DD-2023-118 | Omission of Allowance for maintaining the equipment for use by the Engineer. | Engineer | -184000 | [5 empty] | AW 14
15 | DD-2023-118 | Omission of the allowance for disconnection and clearance the equipment for use by the Engineer. | Engineer | -115000 | [5 empty] | AW 15
16 | DD-2023-118 | IFC Drawings changes | Contractor | 20000000 | [5 empty] | AW 16
17 | DD-2023-118 | Prolongation (As-Built Record from SEC) | Contractor | [6 empty] | AW 17
|  | Total |  | 40785316.5772
-1165663
0
6795182.3115
23526150.2539
-107199.1247
-1028790
-2078855.6387
-28750
-184000
-115000
20000000
Formulas:
Flow of Actions = +[Contractor Proposal]+23
Flow of Actions = +[Forecast/Actual Completion]+12
Forecast/Actual Completion = +[CCF Approval on Aconex]
Forecast/Actual Completion = +[VO Approval on Aconex]
30.04
spoke with Martin about why these CCFs have not started yet. His response was that the Contract is not signed so these cannot be progressed nor workflows can be initiated....makes sense
Note on Z5: Foreast Completion Date for CCF: PMC/Engineer assessment maximum 5 days from the proposal. RFC approval in workflow maximum 18 days. Total maximum 23days
Note on AN5: Forecast Completion Date for VO: 3 days for PMC/Engineer to prepare VO 7 days for VO approvals on workflow 2 days to obtain wet signature from DGCL + Contractor Total maximum 12days

## Do not delete (hidden)
Type of Change | Status of CCF | Action Owner | Status of CCF |  | Provisional Sum
Visual | Approved | Contractor | Proposal Under Assessment with Engineer/PMC | Assessment for VO with Contractor | Yes
Non-Visual | Cancelled | Engineer | Contractor Change Proposal Rejected/Cancelled | Assessment for VO with Engineer | No
| Pending | PMC | CCF Assessment Under Process with Engineer | Assessment for VO with PMC
|  | DGCL | CCF Draf UnderProcess with PMC | VO Drafting under process with Engineer
|  | Closed | CCF Under Review with DGCL | Draft VO under Review with PMC
|  |  | CCF Workflow to be initiated by PMC | VO workflow to be initiated by PMC
|  |  | CCF in the workflow | VO Under Workflow
|  |  | CCF Rejected by DGCL | VO Rejected by DGCL
|  |  | CCF Approved by DGCL | VO Approved by DGCL
|  |  | On Hold | VO for Wet Signature with DGCL
VO to be signed by the Contractor
Closed - VO singned by Contractor
On Hold