## Actual For Week 52
Projects Name: | [7 empty] | DG II - INFRA PACKAGE - 1 | [10 empty] | Week No. | Week 52
Projects no: | [7 empty] | DD-2023-118 | [10 empty] | Period | 4th jan to 9th jan 2025
Weekly concrete schedule
SN | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Location |  |  | Concrete Element | Discipline | Class | Supplier | [5 empty] | Remarks
[7 empty] | Area | Road/Structure Name | Station
[14 empty] | Weekly Planed qty |  | Actual Pouring Qty
[14 empty] | Qty (m³) | Cumulative Qty (m³) | Date of Pouring | Qty (m³) | Cumulative Qty (m³)
[7 empty] | Area civic quarter 1b. | PWPS-01 | Pump room wall(upto 1.2m H) | Pump Room | Civil | OPC C-35 GGBS 65% | UBCC | 35 | 35 |  | 0 | 0
[7 empty] | 1e-North Center | PWPS-02 | Reservior Blinding | Reservior | Civil | C21-OPC | UBCC | 350 | 385 | 07-01-2025 & 09-01-2025 | 310 | 310
[7 empty] | 1d-Northern West | Road-03 | MH-39-11-6-5 | Manhole Blinding (1 manholes) | SW-Storm water | C-21 SRC | UBCC | 1 | 386 | 2025-01-09 | 1 | 311
[7 empty] | Medai 1a | Road-11 | Raiser KI-787,KI-799 | Kerb Inlet | SW-Storm water | C-21 SRC | UBCC | 2 | 388 | 2025-01-05 | 1.5 | 312.5
[7 empty] | Medai 1a | Road-11 | MH-3,MH-4 ,MH-5,MH-6 | Benching | SW-Storm water | C-21 SRC | UBCC | 3 | 391 | 2025-01-07 | 1 | 313.5
[7 empty] | Medai 1a | Road-11 | MH 3-15 | Manhole Blinding (1 manholes) | SW-Storm water | C-21 SRC | UBCC | 1 | 392 | 2025-01-07 | 1 | 314.5
[7 empty] | Medai 1a | Road-11 | MH 31,MH 32,MH 33 | Manhole Blinding (3 manholes) | SG-Sewer | C-21 SRC | UBCC | 2 | 394 | 2025-01-07 | 1 | 315.5 | MH-33 DONE
[7 empty] | 1a-Media | AL_PR_R_00_3 | MH-18, MH-17, MH-5-19, MH-5-18, MH-5-17, MH-5-16, MH-5-15, MH-5-14, MH-5-13,MH-9 | Manhole Blinding (10 manholes) | SW-Storm water | C-21 SRC | UBCC | 7 | 401 |  | 0 | 315.5
[7 empty] | 1d-Northern West | Road-03 | MH 36,SDC 1 | Manhole Blinding (2 manholes) | SG-Sewer | C-21 SRC | UBCC | 1 | 402 |  | 0 | 315.5
[7 empty] | 1a-Media | Road-11 | KI 613,CB 232,Ki 515,KI 188,KI 114 ,KI 316 | Kerb Inlet | SW-Storm water | C-21 SRC | UBCC | 3 | 405 | 2025-01-07 | 2 | 317.5 | KI114, KI316, CB232
[7 empty] | 1a-Media | Road-11 | MH 10,MH 9,MH 8 | Manhole Blinding (3 manholes) | SG-Sewer | C-21 SRC | UBCC | 2 | 407 | 2025-01-05 | 3 | 320.5
[7 empty] | 1c-Boulevard North West | Road-05 | KI 715,KI 703 | Kerb Inlet | SW-Storm water | C-21 SRC | UBCC | 1 | 408 |  | 0 | 320.5
[7 empty] | 1a-Media | Road-11 | MH 8 | Manhole Blinding (1 manholes) | SW-Storm water | C-21 SRC | UBCC | 1 | 409 | 2025-01-05 | 1 | 321.5
[7 empty] | 1a-Media | Road-11 | MH 11,MH 12,MH-13, MH-14, MH-15 | CONCRETE COLLAR (5 manholes) | SW-Storm water | C-35 SRC | UBCC | 2 | 411 | 2025-01-07 | 6 | 327.5
[7 empty] | 1a-Media | Road-11 | MH3, MH-5, MH-6 | CONCRETE COLLAR (3 manholes) | SW-Storm water | C-35 SRC | UBCC | 5 |  | 2025-01-05 | 5 | 332.5
[7 empty] | 1a-Media | Road-11 | MH-12, MH-15, MH-16, MH-17, MH-18, MH-19 | CONCRETE COLLAR ( 6manholes) | SG-Sewer | C-35 SRC | UBCC | 9 |  | 2025-01-09 | 9 | 341.5
[7 empty] | 1a-Media | Road-11 | MH 11,MH 12,MH-13, MH-14, | Benching | SW-Storm water | C-35 SRC | UBCC | 1 |  | 2025-01-09 | 1 | 342.5

## Plan For Week 53
Projects Name: | [7 empty] | DG II - INFRA PACKAGE - 1 | [10 empty] | Week No. | Week 53
Projects no: | [7 empty] | DD-2023-118 | [10 empty] | Period | 11th jan to 16 jan 2025
Weekly concrete schedule
SN | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Location |  |  | Concrete Element | Discipline | Class | Supplier | [5 empty] | Remarks
[7 empty] | Area | Road/Structure Name | Station
[14 empty] | Weekly Planed qty |  | Actual Pouring Qty
[14 empty] | Qty (m³) | Cumulative Qty (m³) | Date of Pouring | Qty (m³) | Cumulative Qty (m³)
1 | [6 empty] | 1c-Boulevard North-west | AL_PR_R_00_11 | MH-3-2, MH-3-3, MH-3-4, MH-3-5, MH-3-6,MH-3-7, MH-3-8, MH-3-9, MH-3-10, MH-3-11, MH-3-12, | Concrete Collar(11 Manholes) | SW-Storm water | C-35 SRC | UBCC | 28 | 28
2 | [6 empty] | 1a-Media | AL_PR_R_00_11 | KI 613,Ki 515,KI 188 | Kerb Inlet | SW-Storm water | C-35 SRC | UBCC | 2 | 30
2 | [6 empty] | 1c-Boulevard North-west | AL_PR_R_00_11 | MH-13, MH-11, MH-20, MH-21, MH-22 | Concrete Collar(5 Manholes) | SG-sewer water | C-35 SRC | UBCC | 10 | 40
3 | [6 empty] | 1a-Media | AL_PR_R_00_11 | MH-12, MH-11,MH-16, MH-19, MH-20, MH-21, | Benching Concrete (6 Manholes) | SG-sewer water | C-25 OPC | UBCC | 3 | 43
4 | [6 empty] | Area civic quarter 1b. | PWPS-01 | Pump room wall(upto 1.2m H) | Pump Room | Civil | OPC C-35 GGBS 65% | UBCC | 35 | 78
5 | [6 empty] | Area civic quarter 1b. | PWPS-01 | Reservoir wall STW-5,STW-1 | Reservoir | Civil | OPC C-35 GGBS 65% | UBCC | 231 | 309
[7 empty] | 1e-North Center | PWPS-02 | Reservior & pump room Blinding | Reservior | Civil | C21-OPC | UBCC | 130 | 439
[7 empty] | 1e-North Center | PWPS-02 | Reservior Screed | Reservior | Civil | C20-SRC | UBCC | 200 | 639