## Sheet1
SWL VOs
SE | Taske | Scope | Instruction Issue date | EI/CCF Reference | EI/CCF Issue Date | Shop drawings submission | Shop Drawing Approval - SWL date | Planned NTS Issue date | NTS Issued date | PL Start Date | PL Finish Date | Actual Finish Date | WIR Submittal date with Photographic Record | WIR Approval date with Photographic Record2 | Handover over to SWL date | Actual Final Sign Off Date | ACONEX Log Uploaded by PMC | Comments
1 | Gate 2B modifications
2 | Road M-04 Diversions
3 | NW-D Diversion – Gyratory Done | 1. Install all signage and speed humps. 2. Earthworks to form Dirt Road across Berm, removal of kerbs and median. (Note: No asphalt required in that location) 3. Earthworks to form Asphalt Road across Berm, removal of kerb. 4. Earthworks to form Dirt Road across Berm, removal of kerbs and median. (Note: No asphalt required in that location) | 2025-02-10 | TBA | TBA | Done |  |  | 2025-02-27 | 2025-02-27 | 2025-03-05 | [6 empty] | The remaining signage will completed after Alssab finished his scope forcastdate to compelete 04-Mar-2025
4 | Grand Mosque Phase 2 | The scope of the proposed change is to construct the Grand Mosque Diversion Phase-2. This work will include the following -Temporary road/traffic diversion - Information / Directional signages - Road repairs (Milling of Ashalt in the required areas and Laying of 70mm of ABC class B - Generally clearance in the new road area - Excavation for the North Haul Road - Disposal of Excavated Material - Backfilling using material issued by the Employer - laying of aggregate base course 20 - Street Lighting Pole 6-8m, single arm 1x120W, 230V, 60Hz.(solar cell) - Removal of existing hardscape - Removal of interlock - Road markings for pedestrian crossing and proposed ramp - Traffic Signages - Directional arrow road markings | In progress | TBA | TBA | [12 empty] | CCF draft was issued to DC ON 17-02-2025
5 | Gate 2K Entry / Exit
6 | ABS Diversion Stage 2
7 | Road M-03 Diversion – ARENA/OPERA | Scope of Work involves the construction of a 9m haul road in parallel with permanent Road 3 works to open Arena / Opera work front. | In progress | TBA | TBA | URGENT | URGENT | URGENT | URGENT | 20.03.25 | 2025-03-11
8 | Gate 2F modifications
9 | DQ Exit / Entry Modifications
10 | Wadi Crossing – Resurfacing